## Projected
|  | 15th Feb | 22nd Feb | 1st Mar | 8th Mar | 15th Mar | 22nd Mar | 29th Mar | 12th Apr | 19th Apr | 26th Apr | 3rd May | 10th May | 17th May | 24th May | 31st May
WP | Task | Wk1 | Wk2 | Wk3 | WK4 | WK5 | WK6 | Easter | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14
Report
Create an account | bar: 15th Feb
Load template | bar: 15th Feb
Read guidelines | bar: 15th Feb to 22nd Feb
Deliverables
Create GIT Account | bar: 15th Feb
Share with lecturer | bar: 22nd Feb
Commit regularly | bar: 1st Mar to 10th May
Record prototype | bar: 22nd Mar to 19th Apr
Upload VIVA | bar: 3rd May to 17th May
Submit report | bar: 24th May
Research Methodology
Hypothesis
Research Questions | bar: 1st Mar
Research Methods | bar: 1st Mar to 8th Mar
Research Pipeline | bar: 8th Mar to 15th Mar
Finalise section in report | bar: 15th Mar to 22nd Mar
Literature Review
Review datasets | bar: 22nd Mar
Review algorithms | bar: 22nd Mar
Review evaluation metrics | bar: 22nd Mar
Finalise section in report | bar: 29th Mar to 12th Apr
Prototype
Find tutorial | bar: 22nd Mar
Replicate tutorial | bar: 22nd Mar to 29th Mar
Create custom dataset | bar: 29th Mar to 12th Apr
Tweek prototype | bar: 12th Apr
Generate evaluation results | bar: 12th Apr to 19th Apr
Discussion of Results
Write prototype evaluation | bar: 19th Apr
Write dataset evaluation | bar: 19th Apr to 26th Apr
Write hypothesis testing | bar: 26th Apr
Write project evaluation | bar: 26th Apr to 3rd May
Finalise section in report | bar: 3rd May to 10th May
Other sections (Conclusion, Introduction, Abstract)
Finalise conclusion & recommendations | bar: 17th May
Finalise Introduction | bar: 17th May
Finalise Abstract | bar: 17th May

## Actual
|  | 6th September | 13th September | 20th September | 27th September | 4th October | 11th October | 18th October | 25th October | 1st November | 8th November | 15th November | 22nd November | 29th November | 6th December | 13th December | 20th December | 27th December | 3rd January | 10th January | 17th January | 24th January | 31st January | 7th February | 14th February | 21st February | 28th February | 7th March | 14th March | 21st March | 28th March | 4th April | 11th April | 18th April | 25th April | 2nd May | 9th May | 16th May | 23rd May | 30th May | 6th June | 13th June | 20th June | 27th June
WP | Task | Wk1 | Wk2 | Wk3 | WK4 | WK5 | WK6 | Easter | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42
Report
Create an account
Load template
Read guidelines
Deliverables
Create GIT Account
Share with lecturer
Commit regularly
Record prototype
Upload VIVA
Submit report
Research Methodology
Hypothesis
Research Questions
Research Methods
Research Pipeline
Finalise section in report
Literature Review
Review datasets / assets
Review algorithms
Review evaluation metrics
Finalise section in report
Prototype
Find tutorial / Review existing games
Replicate tutorial
Create custom dataset / assets
Develop prototype
Generate evaluation results
Discussion of Results
Write prototype evaluation
Write dataset evaluation
Write hypothesis testing
Write project evaluation
Finalise section in report
Other sections (Conclusion, Introduction, Abstract)
Finalise conclusion & recommendations
Finalise Introduction
Finalise Abstract